## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes | Status
2016-11-30 | Conception / Brainstorm | Make Project Plan, main goals, brainstorm, basic dicussion. | All | Throughout the past week we have brainstormed and discussed the basic idea and functionality of what we want this app to do. we have started the project plan, communications plan.
12/01/2016 12/04/2016 | Whiteboard/Design Session | Discuss the end goal of the application, Determine what will be in our first release. | All
2016-12-04 | Create basic workout Plan | Create workout plan, spreadsheet, mathmatical calculations of max percentages ranging 0-100% increasing by 5 percent increments | Jon | Created the workout for testing and week 1, thought of a point system calculator, created a percent of max weight calculator and found a % to weight chart.
2016-12-05 | Begin the new workout plan and test the point to weight scale/system. | Test and fix any first day issues in regards to the percentages and point system. | All | The point to weight scale system will detrimental to the success of the application.
2016-12-09 | update Max weights | put all of the recorded Max weights into the percent calculator | all | done
2016-12-11 | create week 2 workout | create week 2 workout and plug in the rep to % amounts ALSO add point system into the workouts records | all | Updated weights from the past week, created the new week workout with reps and the percentages that we should use. Also came up with a new idea for the point system that gives flexability to the user in selecting weights, but it also helps you get more points the more you push yourself. I feel like this will help retain users who do not enjoy working out as much and who do not like to push themselves too hard.This point system will be still be rewarding to them and will help keep " ON THE FENCE USERS interested."
2016-12-12 | finalize a point system | finalize and use the new point system to calcuate our daily points | all | We finalized the point system logic and tested it with our recorded weights the logic is: Points = (reps lifted - griven reps) + (percentage done - given percentage) + CB*
2016-12-13 | Design / flow chart / wire frame | Create a step through flow chart of how the system/ site/ app will work | all | Created and Activity diagram that shows the initial step through and flow of the application.
2016-12-18 | create workout for week 3 | get the workout made for the week to come | all
2016-12-18 | create UI / page layouts | create UI for the wire frames | all
2016-12-18 | create final wireframe/ flow chart/ activity Diagram | create final wireframe/ flow chart/ activity Diagram | all

## Communications Plan
Communications Plan:
Stakeholder | what do we need to tell them | How do we communicate | Frequency | Notes | Priority
Fidelity HR | Disclose/ ask about the application and any permissions | Phone | Once | We need to find out the Fidelity HR Number | Medium
Team | we need to discuss topics on the Project Plan | phone, skype, text,drive | Bi-weekly | track status and progression. | medium